## Slide 1: LaSalle Rowing Club
Strategic Plan Supplement
October 6, 2023

## Slide 2: About the Strategic Plan Supplement
This document is a supplement to the Strategic Plan. It aids with implementation.
This tool includes:
  strategic plan contents
  action planning tables for each objective, with timelines, responsible persons (recommended), resources, and success indicators
  summary of results from strategic planning process
  a list of recommended roles to implement the strategic plan
  key resources (e.g., draft volunteer/ committee recruitment flyer, draft Terms of Reference, procedure development tool, communications planning tools, member feedback tools [survey], volunteer engagement resources, etc.)
    Including resources does not imply my support for related products
  communications supports for sharing the strategic plan with members and community are included separately

## Slide 3: Key Statements
Statement Type | Purpose | Draft Statement
Vision | The ‘North Star’; the ideal world you’re trying to achieve. | By 2034, Windsor-Essex is home to a vibrant community of rowers with ample opportunities to row for fun, fitness, and competition.
Mission | What you are doing to achieve your vision. Your current hypothesis about how you will get there. | LaSalle Rowing Club fosters a love of rowing in our members and our community.
Values | What you prioritize when you make decisions and interact with each other. | Teamwork: We work together, on and off the water. Inclusion: We ensure opportunities are inclusive of all perspectives and abilities. Transparency: We function best when everyone shares information they need to fully participate. Passion: We share our love of rowing with each other and the community.

## Slide 4: LaSalle Rowing Club Fosters a Love of Rowing in our Members and our Community by…
Building
Building a strong foundation for growth through clear, transparent, and effective internal processes.
Expanding
Expanding our reach by engaging the community in our love of rowing.
Growing
Growing infrastructure to enhance opportunities for rowing in Windsor-Essex County.

## Slide 5: We build a strong foundation for growth through clear, transparent, and effective internal processes which include:
ensuring that all members embrace our vision, mission, and values
1
Town Hall for members and key stakeholders to showcase the strategic plan
Publishing our key statements on our website, in the boathouse, in the newsletter, and on social media
Creating a welcome package for new and prospective members that includes the key statements
communicating the right information with our members at the right time
2
Including key policies, procedures, and dates in the welcome package
Conducting a planning cycle at the end of each season and communicating plans with members
Holding regular Town Halls to share news with and gather feedback from members
documenting all procedures and creating a system for revising them
3
Creating an ad-hoc committee to document current procedures
Designing a process for identifying the need for new procedures and documenting them
Communicating procedures in a consistent and accessible way

## Slide 6: We expand our reach by engaging the community in our love of rowing, through:
Spreading the word about LRC throughout the community
1
Creating a committee to support external communications
Developing a communication strategy for social media, website, community calendars, and earned media
Regularly updating key communications channels
Finding unique and mutually beneficial opportunities to share with the community
2
Developing a quarterly calendar of community events and attending relevant ones
Teaching community members and fitness leaders proper erging techniques
Developing a volunteer team and event engagement strategies
Building partnerships to increase our footprint across the community
3
Engaging the Town of LaSalle to identify opportunities
Building relationships with secondary and post-secondary education

## Slide 7: We grow our infrastructure to enhance opportunities for rowing in Windsor-Essex County by:
increasing the number and quality of boats
1
Purchase a new safety boat
Seek out funding opportunities to support new purchases
Build relationships with other clubs for potential resale opportunities
developing a boat life-cycle process
2
Convene an ad-hoc committee to establish boat life-cycle process
Determine required funding to support boat life-cycle
Identify a short, medium, and long-term asset (boat) development plan
increasing the physical footprint of the club
3
Conduct an internal prioritization process for growth options
Engage Town of LaSalle in discussions and planning regarding the physical footprint
Develop strategy to increase physical footprint

## Slide 8: We build a strong foundation for growth through clear, transparent, and effective internal processes

## Slide 9: Ensuring that all members embrace our vision, mission, and values
Goal | Action | Timeline | Responsible | Resources | Success Measure
Hosting town hall for members and key stakeholders to showcase the strategic plan | Host town hall or align with existing event (e.g. banquet) | Fall 2023 | Board | Location, refreshments (if desired), volunteer organizers | Town hall hosted
 | Socialize key statements and strategic plan |  | Board | Printing, swag (if desired), displays | Member feedback form (% members who support)
 | Use town hall to engage new volunteers |  | Member engagement lead | Description of volunteer opportunities, sign up mechanisms, leads for volunteer groups | # of new volunteers
Publishing our key statements on our website, in the boathouse, in the newsletter, and on social media | Publish in key places as described | Fall 2023 -Winter 2024 | Internal communications lead (secretary?) and external communications lead | Signs/ plaques, website, newsletter, social media posts | Key statements published on website, in boathouse, in newsletter, and on social media
Creating a welcome package for new and prospective members that includes the key statements | Convene ad-hoc committee to develop package | Winter 2024 | Member engagement lead | Location, time | Committee convened
 | Identify and develop key content for welcome package | Winter 2024 | Ad-hoc committee chair |  | Content identified and developed, includes key statements
 | Share welcome package with new members | Spring 2024 | New member lead | Mechanism to share – website or print | Welcome packaged shared with all new and prospective members

## Slide 10: Communicating the right information with our members at the right time
Goal | Action | Timeline | Responsible | Resources | Success Measure
Including key policies, procedures, and dates in the welcome package | See welcome package creation on previous page |  |  |  | 
Conducting a planning cycle each season and communicating plans with members | Set a date(s) for planning meetings | Fall 2023 - Winter 2024 | Board President | Location, time | Planning meeting dates set
 | Develop planning cycle process | Fall 2023 | Board | Time | Planning cycle process clearly defined
 | Hold planning meetings annually | Fall-Winter annually | Board | Time | At least one planning meeting per year
 | Communicate annual plan with members | Spring annually | Internal communication lead | Newsletter, printing, schedule in boathouse | Annual plan communicated at start of season
 | Communicate annual plan with public | Spring annually | External communication lead | Website, social media, community calendars | Annual plan communicated at start of season
Holding regular Town Halls to share news with and gather feedback from members | Develop a member engagement committee | Fall 2023 - Winter 2024 | Member engagement lead | Time | Committee created
 | Determine schedule for regular town halls | By Spring 2024 | Member engagement committee | Time | Schedule developed
 | Host town halls according to schedule | Spring 2024 and ongoing | Member engagement committee | Location, guest speakers (if desired), meeting content | Member feedback

## Slide 11: Documenting all procedures and creating a system for revising them
Goal | Action | Timeline | Responsible | Resources | Success Measure
Creating an ad-hoc committee to document current procedures | Recruit ad-hoc committee | Fall 2023 | Board | Time | Committee members recruited
Designing a process for identifying the need for new procedures and documenting them | Identify list of procedures to be developed | Winter - Spring 2024 | Procedure committee | Time | List of procedures developed
 | Develop procedures using ‘procedure party’ tool | Beginning winter 2024, ongoing | Procedure committee | Time, location | % of procedures developed
 | Identify process for recommending new procedures | Winter 2024 | Procedure committee | Time | Process developed and communicated
Communicating procedures in a consistent and accessible way | Communicate procedures with members | Winter 2024 ongoing | Member engagement lead, internal communication lead | Welcome package, signs, internal communications | All procedures are communicated with existing members and new members; members understand procedures

## Slide 12: We increase our reach by engaging the community in our love of rowing

## Slide 13: Spreading the word about LRC throughout the community
Goal | Action | Timeline | Responsible | Resources | Success Measure
Creating a committee to support external communications | Recruit committee members | Fall 2023 | Board | Time | Committee members recruited
Developing a communication strategy for social media, website, community calendars, and earned media | Develop communication strategy for all channels | Fall - Winter 2024 | External communications committee | Time | # committee meetings, communication strategy developed
 | Implement communications strategy | Beginning winter 2024, ongoing | External communications committee | Time | Strategy implemented, implementation monitored, strategy revised as required
Regularly updating key communications channels | Develop lead and backup for all key communications channels | Winter 2024 ongoing | External communications committee | Communications strategy, shared access | Communications channels updated according to strategy

## Slide 14: Finding unique and mutually beneficial opportunities to share with the community
Goal | Action | Timeline | Responsible | Resources | Success Measure
Developing a quarterly calendar of community events and attending relevant ones | Research community events | Winter 2024 | Community engagement lead | Time | List created
 | Identify events to attend | Winter 2024 and annually | Community engagement lead | Time | Events identified
 | Engage member volunteers to attend events | Winter 2024 ongoing | Community engagement lead | Time, internal communication lead | # volunteers recruited, % of events attended from identified list
Teaching community members and fitness leaders proper erging techniques | Build a network of fitness leaders | Fall 2024 | Community engagement lead | Time | # of leaders identified
 | Identify opportunities to teach erging techniques (schools, gyms, etc.) | Beginning winter 2025, ongoing | Community engagement lead | Time | # of opportunities identified
 | Create and implement a schedule for teaching erging | Beginning winter 2025, ongoing | Community engagement lead | Time, erg equipment, trailer (?) | # of teaching opportunities
Developing a volunteer team and event engagement strategies | Engage volunteers to support community engagement | Winter 2024 ongoing | Community engagement lead | Recruitment tools, leadership, events to support | # volunteers engaged
 | Build volunteer engagement model and identify resource needs | Fall 2024 - Winter 2025 | Member engagement lead and community engagement lead | Time, sample models from other clubs/ groups | Model produced, change in # volunteers engaged, # of events resourced with volunteers

## Slide 15: Building partnerships to increase our footprint across the community
Goal | Action | Timeline | Responsible | Resources | Success Measure
Engaging the Town of LaSalle to identify opportunities | Identifying key officials and sharing the Strategic Plan | Fall 2023 – Winter 2024 | Board President | Time | # of contacts
 | Setting up meetings to share the Strategic Plan | Fall 2023 – Winter 2024 | Board | Time | # people met with
 | Building opportunities to partner with Town | Winter 2024 ongoing | Board | Time | # of new opportunities identified, # of opportunities implemented
Building relationships with secondary and post-secondary education | Developing a list of school contacts | Spring 2024 | School engagement lead | Time | List completed
 | Clarifying opportunity for school engagement at each level | Winter 2024 | School engagement lead, Board | Time | Document/ tool created
 | Inviting schools to participate in opportunity | Fall 2024 – Winter 2025 start | School engagement lead | Time, opportunity | # schools engaged, # students engaged, # new members

## Slide 16: We grow our infrastructure to enhance opportunities for rowing in Windsor-Essex County

## Slide 17: Increasing the number and quality of boats
Goal | Action | Timeline | Responsible | Resources | Success Measure
Purchase a new safety boat | Price out options | Fall 2023 | Board & treasurer | Time | Options detailed
 | Recommend option to board | Winter 2024 | Board | Time | Purchase approved
 | Purchase upon approval | Spring 2024 | Treasurer | Funds, truck/ trailer | Purchase completed
Seek out funding opportunities to support new purchases | Create notification (e.g., Google alert) for funding opportunities | Winter 2024 | Development lead | Time | Notification/ alert created
 | Apply for relevant funding opportunities | Beginning winter 2024, ongoing | Development lead | Time | # of opportunities applied for, $ funds received
Build relationships with other clubs for potential resale opportunities | Identify clubs that have boat lifecycle process beyond ours | Fall 2024, ongoing | Infrastructure lead | Club connections, time | Boat lifecycle information
 | Circulate lifecycle so other clubs know when we may be interested in purchasing | Fall 2024, ongoing | Infrastructure lead | Lifecycle process | # used boats purchased

## Slide 18: Developing a boat life-cycle process
Goal | Action | Timeline | Responsible | Resources | Success Measure
Convene an ad-hoc committee to establish boat life-cycle process | Invite volunteers | Winter-Spring 2024 | Infrastructure lead | Time | # volunteers
 | Determine lifecycle of existing boats | Spring 2024 | Infrastructure committee | Time, boat information | Spreadsheet created
 | Identify process for updating lifecycle information | Spring - Summer 2024 | Infrastructure committee | Time | Process developed
Determine required funding to support boat life-cycle | Generate quotes for existing and short-term boat needs | Summer - Fall 2024 | Infrastructure lead | Quotes | Quotes received
 | Identify funding opportunities to support boat purchases | Fall 2024, ongoing | Infrastructure lead, Development lead | Time, life-cycle | # of opportunities applied for, $ funds received
Identify a short, medium, and long-term asset (boat) development plan | Hold a planning session to identify boat development goals | Fall 2024 | Infrastructure lead | Time, life-cycle, location, planning tools | Asset development plan completed, monitored

## Slide 19: Increasing the physical footprint of the club
Goal | Action | Timeline | Responsible | Resources | Success Measure
Conduct an internal prioritization process for growth options | Update list growth opportunities | Fall 2025 | Board | Time | Opportunities detailed
 | Engage members to prioritize | Fall 2025 | Board | Time, town hall or survey | Prioritization completed
Engage Town of LaSalle in discussions and planning regarding the physical footprint | See “build partnerships” activity |  |  |  | 
Develop strategy to increase physical footprint | Engage ad-hoc committee | Winter 2026 | Ad-hoc committee chair | Time | Committee engaged
 | Develop physical growth strategy | Winter 2026 and ongoing | Ad-hoc committee chair | Time, updated growth opportunities, relationships (e.g., with Town) | Strategy completed with success measures

## Slide 20: Results from Strategic Planning Process
In August 2023, we engaged members, Board, and partners:
  We heard from 28 current and former members, via survey and interviews (in person and phone).
  We heard from 8 Board members and coaches via online survey.
  We spoke with 10 community partners representing Row Canada, Row Ontario, partner organizations and clubs (one additional interview is pending).
  We are in the interview process with staff and elected officials with the Town of LaSalle.

## Slide 21: Community Feedback
LRC is at its best when…
It’s giving people the opportunity to row
Examples of our excellence…
The water is good
We’re working together
We’re being social
Volunteers are engaged
Everyone is pitching in
Para Rowing
Great people who love the sport
People help each other
We all help with the shells
We welcome all skills and abilities
We have strong coaches
Committed volunteers
Grants to support the work
We’re recognized for advances in para rowing

## Slide 22
Community Feedback
If resources were not a barrier…
Ideal future…
Potential opportunities…
Paid coaches
Paid staff
Bigger boathouse
More boats
Indoor erg room, workout room, tanks
Broader community introduced to rowing
Rowing contributes to healthy lifestyle
More connections and social opportunities
Inclusive, regardless of age, ability, race, etc.
Robust recreational and competitive programs for various groups
Engaged members with clear volunteer pipeline
Coastal rowing
Moving into high schools more
Summer camps
Partnerships with University
Regatta (contribute to LaSalle tourism)

## Slide 23: Key roles
Title | Role | Lead Name
Internal communications lead | Lead internal communications committee, develop communication plan | 
External communications lead | Lead external communications, develop communication plan | 
New member lead | Welcome new members, maintain early communications | 
Member engagement lead | Lead Town Halls, seek out feedback from members | 
Community engagement lead | Identify community opportunities, coordinate volunteers | 
Ad-hoc committee chairs (procedures, welcome package, boat lifecycle, etc.) | Lead work via ad-hoc committees | 
School engagement lead | Engage local schools, develop engagement plan | 
Development lead | Lead fund development committee, develop fund development plan | 
Infrastructure lead | Lead infrastructure committee, develop infrastructure plan | 

## Slide 24: Key resources
Draft volunteer/ committee recruitment flyer
Draft Terms of Reference
Procedure development tool
Communications planning tools
Member feedback tools (surveys)
List of growth opportunities
Volunteer engagement tools
Social media posts

## Slide 25: Communications Planning Tools
Develop 1-2 SMART goals per season (specific, measurable, achievable, relevant, time-based).
For each goal, decide on the following:
  message
  audience
  medium/ delivery method(s)
  timing
  target/ goal
Resources to help you develop your plan:
  What is a communications plan and why is it important?
  The 5 steps you need for non-profit communications.

## Slide 26: Member Feedback Survey Questions
Purpose: to understand member engagement and identify areas for improvement.
When: Once per year
How: Google forms or other survey tool
Questions:
  How do you feel about rowing now, versus the beginning of the season? (I like rowing more now/ about the same/ I liked rowing more at the beginning of the season)
  What can LaSalle Rowing Club do to improve your experience? (open-ended)
  Would you recommend LaSalle Rowing Club to a friend or colleague? (score of 0-10, see Net Promoter Score to analyze)
  Do you currently volunteer with the Club? (Yes/ no; if no, would you like to?)

## Slide 27: Volunteer Engagement
Event Volunteers
Committee Members
Leads, Coaches, Safety Boat Drivers
Board
General members
As a volunteer-run organization, the Strategic Plan relies on an engaged membership.
All members should understand the available volunteer opportunities, beginning with the welcome package.
Members should be invited to bring their skills and passions to the club.
Volunteers may progress through the rings to the left in terms of their level of engagement. (Although they may start and stop at any point.)
Follow volunteer engagement practices

## Slide 28: Growth Opportunities (for future)
Youth summer camp
Education institutions/ schools
Provincial youth engagement initiative
Coastal rowing
Expansion within region (additional sites)
Town of LaSalle footprint

## Slide 29
Procedure Name
Does this capture how we do things? (If new, how do we do things?)
If I was new to rowing, would I understand how to apply this policy?
Are there any times where this procedure wouldn’t apply?
Does this give us enough information to make a clear decision?
Who does this procedure apply to? Who needs to know?
How should we communicate this procedure?
Details to include:
Purpose
Responsible
Summary
Step-by-step
Review timeline
Related procedures

## Slide 30: Terms of Reference
Committee Name: Internal Communications
Type: Advisory committee
Purpose: To plan and manage communications with members and prospective members.
Responsibilities: Newsletter, welcome package, internal communications plan
Authority: Board approves annual communications plan, committee has authority to execute.
Composition: Minimum of 3 members, no maximum. Volunteers accepted. (follow existing rules for quorum, Board member requirements, chairs, etc.)
Meetings: Committee to determine meeting frequency, date, location, communication.
Reporting: Committee presents annual communications plan to Board and submits summary report annually.
Resources and budget: Developed during planning with Board.
Review: Follow existing rules for review frequency and responsibilities.

## Slide 31: Terms of Reference
Committee Name: External Communications
Type: Advisory committee
Purpose: To plan and manage communications with the community.
Responsibilities: Social media management, website, community events, external communications plan.
Authority: Board approves annual communications plan, committee has authority to execute.
Composition: Minimum of 3 members, no maximum. Volunteers accepted. (follow existing rules for quorum, Board member requirements, chairs, etc.)
Meetings: Committee to determine meeting frequency, date, location, communication.
Reporting: Committee presents annual communications plan to Board and submits summary report annually.
Resources and budget: Developed during planning with Board.
Review: Follow existing rules for review frequency and responsibilities.

## Slide 32: Terms of Reference
Committee Name: Member engagement
Type: Advisory committee
Purpose: To support new members and identify opportunities for improvement.
Responsibilities: Town hall planning and execution, member support, annual member survey, includes new member lead
Authority: Execute town halls with Board approval, recommends member engagement opportunities to Board.
Composition: Minimum of 3 members, no maximum. Volunteers accepted. (follow existing rules for quorum, Board member requirements, chairs, etc.)
Meetings: Committee to determine meeting frequency, date, location, communication.
Reporting: Committee reports to Board and maintains transparent relationship with Board.
Resources and budget: Developed during planning with Board.
Review: Follow existing rules for review frequency and responsibilities.